# Tobacco Prevention and Education Program Internship Outline

The Clackamas County Public Health Division (CCPHD) Tobacco Prevention and Education Program (TPEP) works to prevent and reduce tobacco use, promote tobacco-free communities, reduce the influence of tobacco product marketing, and encourage tobacco users to quit.

In collaboration with TPEP Program Planners, an intern will support tobacco prevention programming in Clackamas County.

## Secondhand Smoke Assessment

The purpose of the Secondhand Smoke Assessment is to assess the feasibility of expanding the Indoor Clean Air Act by passing policies that reduce exposure to secondhand smoke in outdoor public places such as downtowns.

This is a multi-pronged project consisting of visual assessments, business surveys, key informant interviews, consumer interviews, and quantitative and qualitative data collection and analysis. TPEP staff are prioritizing five cities to include in this assessment.

An intern will support the Secondhand Smoke Assessment in the following areas:

| Activity | Staff Responsible | Deliverable(s) | Timeline |
| --- | --- | --- | --- |
| Visual Assessments – Use TPEP’s visual assessment data collection tool to observe the number of individuals smoking and/or vaping, the number of pedestrians passing through the observation site, tobacco-related litter at the observation site, and smoking and/or vaping policies (if applicable). Observations will be made at five pre-identified locations in each city from 9:00am – 9:30am, 12:30pm – 1:00pm, and 5:30pm – 6:00pm. Observations may be conducted on the weekends. Note reliable travel is required for this activity. | Intern TPEP staff | Visual assessments and observations completed. Observations input in TPEP’s data log. | Estimated Timeline for Completion: August 2024 – October 2024 % of Time Intern Dedicated to Activity: 40% |
| Business Surveys – TPEP staff will interview five businesses in each city to determine the impact of secondhand smoke on their business. | TPEP staff | Business surveys completed and documented in Survey Monkey. | Estimated Timeline for Completion: July 2024 – October 2024 |
| Key Informant Interviews – TPEP staff will conduct key informant interviews with Chamber of Commerce Presidents/Executive Directors in each city to determine the impact of secondhand smoke on downtown economic success. | TPEP staff | Key informant interviews completed and documented in Survey Monkey. | Estimated Timeline for Completion: July 2024 – October 2024 |
| Data Analysis – Once visual assessments, business surveys, and key informant interviews are complete, compile and organize the data collected. Identify locations in each city where the most smoking/vaping activity was observed. Summarize the implications for secondhand smoke exposure based on the number of pedestrians passing through the observation site and qualitative data from business surveys and key informant interviews | Intern | For each city, create a report summarizing data gathered including themes from business surveys/key informant interviews and visual assessments. Include implications for secondhand smoke exposure and limitations of the data. Based on the results, recommend two cities for TPEP staff to focus consumer outreach and policy change efforts. | Estimated Timeline for Completion: November 2024 – December 2024 % of Time Intern Dedicated to Activity: 40% |

## Support Kit Distribution and Reach

In 2023, TPEP purchased 500 support kits to distribute to community members and staff interested in reducing or quitting their tobacco and nicotine use. A year later, TPEP would like to evaluate where the kits were distributed to inform future cessation outreach efforts.

| Activity | Staff Responsible | Deliverable(s) | Timeline |
| --- | --- | --- | --- |
| Community Member Support Kit Data Analysis and Mapping – Use the Support Kit Survey for Community Members tracker to summarize the distribution of support kits. | Intern | Map the distribution of support kits to community members. Analyze support kit distribution by product(s) used and age range. | Estimated Timeline for Completion: August 2024 – September 2024 % of Time Dedicated to Activity: 10% |
| Employee Support Kit Data Analysis – Use the Support Kit Survey for Employees to summarize employee support kit distribution. Results will inform future employee cessation support and engagement with insurance providers. | Intern | Analyze Clackamas County Employee Support Kit survey data by product(s) used, age range, and insurance type. | Estimated Timeline for Completion: August 2024 – September 2024 % of Time Dedicated to Activity: 10% |

The TPEP intern will also support additional duties as assigned. Such duties include, but are not limited to:

- Attending prevention-related meetings (Clackamas County Prevention Coalition, Oregon Partners for Tobacco Prevention, TPEP Staff Meetings)

- Tobacco prevention research to support projects as needed